## Sheet1
Task no. | Task |  | Resource | Mds | Start date | End date | STATUS | Remarks/Comments
1 | login | Backend | Zamiya | 2 | 2023-05-22 | 2023-05-23 | 90% | Login to Home connection database connectivity
2 | Login page | Frontend | Zamiya | 1 | 2023-05-23 | 2023-05-23 | 100% | Completed
5 | home page | Frontend | Varun | 1 | 2023-05-23 | 2023-05-23 | 100% | Completed
4 | payment | Frontend | Adarsh | 1 | 2023-05-23 | 2023-05-24 | 100% | Completed
6 | registration | Backend | Zamiya | 1 | 2023-05-24 | 2023-05-24 | 90% | Data fetching problem
7 | registration page | Frontend | Zamiya | 1 | 2023-05-25 | 2023-05-25 | 100% | Completed
8 | notification | Frontend | Adarsh | 1 | 2023-05-25 | 2023-05-26 | 100% | Completed
9 | home | Backend | Varun | 1 | 2023-05-26 | 2023-05-27 | 100% | Cpmpleted
10 | payment | Backend | Adarsh | 1 | 2023-05-25 | 2023-05-28 | 90% | Database Connection left
3 | flight detail | Frontend | Varun | 1 | 2023-05-29 | 2023-05-29
11 | flight detail | Backend | Varun | 1 | 2023-05-29 | 2023-05-30
12 | notification | Backend | Adarsh | 1 | 2023-05-27 | 2023-05-31 | 50% | Database Connection left
13 | Admin Signin | Frontend | Varun | 1 | 2023-05-29 | 2023-06-01
12 | Admin Signin | Backend | Varun | 1 | 2023-06-01 | 2023-06-02