## Sheet1
Task no. | Task |  | Resource | Mds | Start date | End date | STATUS | Remarks/Comments
1 | login | Backend | Zamiya | 2 | 2023-05-22 | 2023-05-23 | 90% | Login to Home connection database connectivity
2 | Login page | Frontend | Zamiya | 1 | 2023-05-23 | 2023-05-23 | 100% | Completed
3 | flight detail | Frontend | Varun | 1 | 2023-05-23 | 2023-05-25 | 90% | Merging and connected to home page form left
4 | payment | Frontend | Adarsh | 1 | 2023-05-23 | 2023-05-24 | 100% | Completed
5 | home page | Frontend | Varun | 1 | 2023-05-23 | 2023-05-23 | 100% | Completed
6 | registration | Backend | Zamiya | 1 | 2023-05-24 | 2023-05-24 | 90%
7 | registration page | Frontend | Zamiya | 1 | 2023-05-25 | 2023-05-25 | 100% | Completed
8 | notification | Frontend | Adarsh | 1 | 2023-05-25 | 2023-05-26
9 | home | Backend | Varun | 1 | 2023-05-26 | 2023-05-27
10 | payment | Backend | Adarsh | 1 | 2023-05-25 | 2023-05-25 | 90% | Database Connection left
11 | flight detail | Backend | Varun | 1 | 2023-05-27 | 2023-05-29
12 | notification | Backend | Adarsh | 1 | 2023-05-27 | 2023-05-28